## Cover Sheet
Care Information Exchange - Go Live Assurance Criteria
Guidance Notes
These assurance criteria are used by the Care Information Exchange Steering Group to monitor and control CIE project stage boundaries and as guidance for CIE project teams.
The assurance criteria are divided into 5 gateways. Any criteria not fully met before progressing to the next stage will be carried forward.
The criteria should be presented to the CIE Steering Group with the approval of the Senior Information Risk Owner (SIRO) of the organisation.
Supporting documentation can be found on the CIE website Resources page. Before proceeding with work the latest versions of these documents should be requested from the CIE project manager.
Where an organisation is using CIE for multiple projects a "status" column should be added to each worksheet for each project.
CIE deployments can be grouped into two categories (i) organisation, and (ii) service. To deploy an organisation interface gate 1 will need to be completed for this purpose. When an organisation first deploys CIE to a service within their organisation they will need to complete gate 1 for that purpose even if previously completed for the organisation interface, and then any subsequent gates. Any subsequent service deployments within that organisation will not require the gateway criteria to be resubmitted but they can be used as as local guidance.
Organisation interface deployment (to be completed by project lead for submission to CIE Steering Group) | Proposed go live date | Name of SIRO | Approval date
First service deployment (to be completed by project lead for submission to CIE Steering Group) | Proposed go live date | Name of SIRO | Approval date
Template version | v4_0

## Gate1 - Record creation
No organisation will be authorised to begin creating or updating CIE records (either manually or through system interfaces) until this gateway has been passed.
Record creation and update criteria
[5 empty] | Project 1 | Project 2
Category | Assurance criteria | Type | Requirement | Guidance | Status | Status | Evidence / comment
Operational governance | Clinical and operational agreement to proceed from appropriate levels within organisation. | All | Essential
Information governance | Internal IG approval to proceed. | All | Essential
| Nominate Privacy Officer. | All | Essential | CIE website |  |  | CIE Roles and Responsibilities on CIE website Resources page
| Organisation signed NWL Digital Information Sharing Agreement. | All | Essential | Link to ISA
| Identify any additional datasets to flow to CIE approved by the NWL Digital Governing Group. | All | Essential | CIE website |  |  | CIE data sharing template on CIE website Resources page
| Organisation has passed IG Toolkit level 2. | All | Essential
| Fair processing materials in place 6 weeks prior to moving data. | All | Essential
Communications | Publish internal comms to let staff know patients will have access to their data if registered with PKB elsewhere | Interfaces only | Desirable
Technical | Process for patient record creation documented and tested. | All | Essential
| CIE technical guidance document reviewed and compliance confirmed. | Interfaces only | Essential | CIE website |  |  | CIE Technical Guidance document on CIE website Resources page
| CIE numbering strategy reviewed and compliance confirmed. | Interfaces only | Essential | CIE website |  |  | CIE Numbering Strategy on CIE website Resources page (note NHS number and status conditions)
| Interfaces to send data from local systems to CIE developed and local testing on PKB Sandbox completed. | Interfaces only | Essential |  |  |  | Path Testcode Categories, Path test codes for patient delay and Imperial specialty code mapping on CIE website Resources page
| Multi-source testing completed using PKB Sandbox environment and signed off by organisation and PKB. Plan in place for multi-source QA testing in PKB Prod in accordance with testing strategy. Testing report provided by PKB. | Interfaces only | Essential | CIE website |  |  | CIEHL7IntegrationAssuranceTestScriptDemographics and CIEHL7IntegrationAssuranceTestScriptLaboratoryResults on CIE website Resources page
| PKB integration steps completed. | Interfaces only | Essential | CIE website |  |  | PKB integration steps on CIE website Resources page
Reporting | System reporting requirements defined and tested. | All | Desirable
System support | Information Asset Owner, Application Manager and Privacy Officer identified. | All | Essential | CIE website |  |  | CIE Roles and Responsibilities on CIE website Resources page
| Interface monitoring and support agreed and in place. | Interfaces only | Essential
| Internal process for data corrections agreed and in place. | All | Desirable
| Internal process for patient queries agreed and in place. | Interfaces only | Essential |  |  |  | Sample template available from project manager.

## Gate2 - Staff training
No staff training will begin until this gateway has been passed.
Carried forward criteria
|  |  |  | Project 1 | Project 2
Category | Assurance criteria | Requirement | Guidance | Status | Status | Evidence / comment
Staff training criteria
|  |  |  | Project 1 | Project 2
Category | Assurance criteria | Requirement | Guidance | Status | Status | Evidence / comment
Information governance | Staff account setup, new starters and leavers, and system access workflow documented. | Essential | CIE website |  |  | Generic CIE Process Maps on CIE website Resources page
Technical | Integration to launch CIE from local systems using single sign-on developed and tested. | Desirable
System support | Process agreed and in place for staff user queries and issue resolution. | Desirable
| Team co-ordinator identified at each required team level. | Desirable
PKB Configuration | Teams setup in PKB Sandbox representing the teams required for go live. | Essential
| Care plan templates completed. | Desirable
| Library links added. | Desirable
| Consultations built and added. | Desirable
| Symptom tracking set up. | Desirable
Change management | CIE overview familiarisation sessions held with key team members. | Essential
| Scope of CIE functionality to be used documented and agreed. | Essential | CIE website |  |  | Scope and training requirements template on CIE website Resources page
| Workflows documented and agreed (based on agreed functionalities and data flows). | Essential | CIE website |  |  | Generic CIE Process Maps on CIE website Resources page
| Roles and responsibilities matrix completed. | Essential
Training | Training plan agreed based on scope of functionalities. | Essential | CIE website |  |  | Scope and training requirements template on CIE website Resources page
Testing | Full workflow tested from end to end with user acceptance signed off. | Essential | CIE website |  |  | Generic test scripts on CIE website Resources page

## Gate3 - Staff activation
No staff will be activated until this gateway has been passed.
Carried forward criteria
|  |  |  | Project 1 | Project 2
Category | Assurance criteria | Requirement | Guidance | Status | Status | Evidence / comment
Staff activation criteria
|  |  |  | Project 1 | Project 2
Category | Assurance criteria | Requirement | Guidance | Status | Status | Evidence / comment
Training | Coordinator role training completed. | Essential
| Professional role training completed. | Essential
| Train the trainer training completed. | Essential
| Standard Operating Procedures approved with printouts of most common ones accessible where required. | Desirable
| Quick Reference Guides approved with printouts of most common ones accessible where required. | Desirable | CIE website |  |  | Generic professional and coordinator QRGs on CIE website Resources page
PKB configuration | Configuration for go-live completed (live site created as copy of Sandbox etc.). | Essential
| Messaging defined - contactable professionals identified & set up incl out of office info. | Essential
Evaluation | Evaluation baseline completed and plan for follow-up evaluation agreed. | Desirable
| Plan for reporting CIE usage data for purposes of local evaluation agreed. | Desirable

## Gate4 - Patient activation
No patients will be activated until this gateway has been passed.
Carried forward criteria
|  |  |  | Project 1 | Project 2
Category | Assurance criteria | Requirement | Guidance | Status | Status | Evidence / comment
Patient activation criteria
|  |  |  | Project 1 | Project 2
Category | Assurance criteria | Requirement | Guidance | Status | Status | Evidence / comment
Information governance | Processes in place to enable patients to opt out. | Essential
| Patient sign-up, authentication and activation process documented. | Essential | CIE website |  |  | CIE Patient Enrolment Guide on CIE website Resources page.
Communications | Staff and patient communication documentation created and published. | Essential
System support | Internal process for patient queries agreed and in place. | Essential |  |  |  | Sample template available from project manager.
Evaluation | Evaluation baseline completed and plan for follow-up evaluation agreed. | Desirable
| Plan for reporting CIE usage data for purposes of local evaluation agreed. | Desirable

## Gate5 - Closure
No CIE project will be closed until this gateway has been passed.
Carried forward criteria
|  |  |  | Project 1 | Project 2
Category | Assurance criteria | Requirement | Guidance | Status | Status | Evidence / comment
Project closure criteria
|  |  |  | Project 1 | Project 2
Category | Assurance criteria | Requirement | Guidance | Status | Status | Evidence / comment
System Support | Knowledge transfer from project team to operational team completed | Essential
Evaluation | Evaluation completed and report provided to CIE Steering Group | Desirable
Lessons learned | Lessons learned report provided to CIE Steering Group | Essential

## Version Control
Version | Release date | Summary of changes
1_0 | 2016-09-29 | First release to CIE website
2_0 | 2016-11-08 | Gate 5 - evaluation changed from essential to desirable
3_0 | 2017-04-26 | Gate 1 - added internal staff comms and updated cover sheet, added website URL
4_0 | 2017-05-31 | Gate 1 - added PKB integration steps, added patient query support for interfaces only